## 项目规划器
Gantt Chart
Activity ID | Activity | Depend Activity | Person in Charge | Planned Start Time | Planned Completion Time | Planned Period | Actual Start Time | Actual Completion Time | Actual Period | Complete Percentage
Ⅰ | Preliminary
1.1 | Preliminary Work |  | Yi Lu | 2018-03-07 | 2018-03-08 | 1 | 2018-03-07 | 2018-03-08 | 1 | 100%
Ⅱ | Requirements Analysis
2.1 | Requirements Confirmation |  | Yi Lu | 2018-03-10 | 2018-03-13 | 3 | 2018-03-10 | 2018-03-12 | 2 | 95%
2.2 | Requirement Documents |  | Yi Lu | 2018-03-14 | 2018-03-18 | 4 | 2018-03-14 | 2018-03-17 | 3 | 85%
Ⅲ | Structure Design | Ⅱ
3.1 | Web Framework Design |  | Yukai Jiang | 2018-03-15 | 2018-03-18 | 3 | 2018-03-15 | 2018-03-18 | 3 | 95%
3.2 | Database Design |  | Yukai Jiang | 2018-03-15 | 2018-03-22 | 7 | 2018-03-15 | 2018-03-25 | 10 | 90%
Ⅳ | System Design
4.1 | Developing Prototype | Ⅱ | Ruolin Huang | 2018-03-20 | 2018-03-25 | 5 | 2018-03-20 | 2018-03-24 | 4 | 70%
4.2 | UI Design | 4.1 | Ruolin Huang | 2018-03-18 | 2018-03-22 | 4 | 2018-03-20 | 2018-03-25 | 5 | 80%
Ⅴ | Coding
5.1 | Modular Design | 4.1 | Yukai Jiang | 2018-03-27 | 2018-03-29 | 2 | 2018-03-28 | 2018-03-31 | 3 | 100%
5.2 | Modular1 Programming | 5.1 | Ruolin Huang | 2018-04-01 | 2018-04-06 | 5 | 2018-04-01 | 2018-04-09 | 8 | 90%
5.3 | Modula2 Programming | 5.1 | Yuan Li | 2018-04-01 | 2018-04-08 | 7 | 2018-04-01 | 2018-04-06 | 5 | 100%
5.4 | Modula3 Programming | 5.1 | Yuan Li | 2018-04-01 | 2018-04-13 | 12 | 2018-04-01 | 2018-04-16 | 15 | 95%
5.5 | Modula4 Programming | 5.1 | Mingxi Chen | 2018-04-09 | 2018-04-24 | 15 | 2018-04-09 | 2018-04-29 | 20 | 100%
Ⅵ | Testing
6.1 | Make Testing Plan | Ⅱ&Ⅴ | Yukai Jiang | 2018-05-01 | 2018-05-05 | 4 | 2018-05-03 | 2018-05-06 | 3 | 80%
6.2 | Perform Tests | 6.1 | Kefei Wu | 2018-05-03 | 2018-05-13 | 10 | 2018-05-05 | 2018-05-13 | 8 | 95%
6.3 | Correct and Optimization | 6.2 | Xinying Wu | 2018-05-15 | 2018-05-20 | 5 | 2018-05-14 | 2018-05-18 | 4 | 90%
Ⅶ | Prpject Management | Ⅱ
7.1 | Make Management Plan |  | Yi Lu | 2018-04-11 | 2018-04-14 | 3 | 2018-04-12 | 2018-04-15 | 3 | 85%
7.2 | Risk&Cost Management | 7.1 | Yi Lu | 2018-04-16 | 2018-04-24 | 8 | 2018-04-18 | 2018-04-28 | 10 | 95%
Ⅷ | Project Acceptance | Ⅶ&6.3
8.1 | Acceptance Test |  | Kefei Wu | 2018-05-20 | 2018-05-25 | 5 | 2018-05-20 | 2018-05-23 | 3 | 100%
8.2 | Final Optimization |  | Xinying Wu | 2018-05-26 | 2018-05-30 | 4 | 2018-05-25 | 2018-05-30 | 5 | 95%
8.3 | Document Organization |  | Yi Lu | 2018-05-15 | 2018-05-30 | 15 | 2018-05-15 | 2018-06-05 | 20 | 100%

## 甘特图
Activity | Planned Start Time | Planned Period | Activity | Actual Start Time | Actual Period
Preliminary Work | 2018-03-07 | 1 | Preliminary Work | 2018-03-07 | 1
Requirements Confirmation | 2018-03-10 | 3 | Requirements Confirmation | 2018-03-10 | 2
Requirement Documents | 2018-03-14 | 4 | Requirement Documents | 2018-03-14 | 3
Web Framework Design | 2018-03-15 | 3 | Web Framework Design | 2018-03-15 | 3
Database Design | 2018-03-15 | 7 | Database Design | 2018-03-15 | 10
Developing Prototype | 2018-03-20 | 5 | Developing Prototype | 2018-03-20 | 4
UI Design | 2018-03-18 | 4 | UI Design | 2018-03-20 | 5
Modular Design | 2018-03-27 | 2 | Modular Design | 2018-03-28 | 3
Modular1 Programming | 2018-04-01 | 5 | Modular1 Programming | 2018-04-01 | 8
Modula2 Programming | 2018-04-01 | 7 | Modula2 Programming | 2018-04-01 | 5
Modula3 Programming | 2018-04-01 | 12 | Modula3 Programming | 2018-04-01 | 15
Modula4 Programming | 2018-04-09 | 15 | Modula4 Programming | 2018-04-09 | 20
Make Testing Plan | 2018-05-01 | 4 | Make Testing Plan | 2018-05-03 | 3
Perform Tests | 2018-05-03 | 10 | Perform Tests | 2018-05-05 | 8
Correct and Optimization | 2018-05-15 | 5 | Correct and Optimization | 2018-05-14 | 4
Make Management Plan | 2018-04-11 | 3 | Make Management Plan | 2018-04-12 | 3
Risk&Cost Management | 2018-04-16 | 8 | Risk&Cost Management | 2018-04-18 | 10
Acceptance Test | 2018-05-20 | 5 | Acceptance Test | 2018-05-20 | 3
Final Optimization | 2018-05-26 | 4 | Final Optimization | 2018-05-25 | 5
Document Organization | 2018-05-15 | 15 | Document Organization | 2018-05-15 | 20