## YearProfit
5-year Profit Statement
(): represent negative
|  | Remark | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
| Revenue |  | 1550000 | 1980000 | 2280000 | 2670000 | 3150000
| (Cost of goods sold) |  | 970300 | 1246300 | 1046300 | 1153300 | 1173400
| Gross profit |  | 579700 | 733700 | 1233700 | 1516700 | 1976600
| (SG&A expense) |  | 315000 | 320000 | 340000 | 330000 | 325000
| (Research&Deployment) |  | 0 | 0 | 0 | 0 | 0
| (Depreciation expense) | Acceleration of depreciation | 67000 | 22000 | 6000 | 36667 | 12222
| (Amortization expense) | Acceleration&Intangible assets | 200 | 180 | 962 | 865.8 | 779.22
| Operating profit(EBIT) |  | 197500 | 391520 | 886738 | 1149167.2 | 1638598.78
| (Interest expense):Borrow 300000 from bank | Annual Interest rate=4.9% | 14026.24 | 12556.24 | 11086.24 | 9614.84 | 8146.24
| Income before tax |  | 183473.76 | 378963.76 | 875651.76 | 1139552.36 | 1630452.54
| (Tax) | Corporate Income Tax+VAT+Business tax and surcharges | 80801.8439 | 159395.6399 | 385637.0351 | 471858.8593 | 618051.2986
| Income from main operations |  | 102671.9161 | 219568.1201 | 490014.7249 | 667693.5007 | 1012401.2414
| Earnings (losses) from other operations, net of tax | About trading securities | 0 | 0 | 0 | -400000 | -384000
| Net income |  | 102671.9161 | 219568.1201 | 490014.7249 | 267693.5007 | 628401.2414
| ROI |  | 5.134% | 8.783% | 19.6% | 10.71% | 25.14%
| (Dividends) |  | 0 | 100000 | 200000 | 20000 | 500000
| ΔRetained return |  | 102671.9161 | 119568.1201 | 290014.7249 | 247693.5007 | 128401.2414
Appendix about tax
|  | Remark | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
| Corporate Income Tax | Tax Rate=25% | 45868.44 | 87240.94 | 218912.94 | 254888.09 | 307613.135
| VAT | Tax Rate=17%
| Sales Tax |  | 31190.5392 | 64423.8392 | 148860.7992 | 193723.9012 | 277176.9318
| Input tax |  | 0 | 0 | 0 | 0 | 0
| Payable VAT |  | 31190.5392 | 64423.8392 | 148860.7992 | 193723.9012 | 277176.9318
| 3% Tax Burden |  | 5504.2128 | 11368.9128 | 26269.5528 | 34186.5708 | 48913.5762
| Tax Refund (Immediate Refund) |  | 25686.3264 | 53054.9264 | 122591.2464 | 159537.3304 | 228263.3556
| Business Tax and Surcharges |  | 3742.8647 | 7730.8607 | 17863.2959 | 23246.8681 | 33261.2318
| Building Tax(VAT based) | Tax Rate=7% | 2183.3377 | 4509.6687 | 10420.2559 | 13560.6731 | 19402.3852
| Education Surcharge(VAT based) | Tax Rate=3% | 935.7162 | 1932.7152 | 4465.824 | 5811.717 | 8315.308
| Local Education Surcharge(VAT based) | Tax Rate=2% | 623.8108 | 1288.4768 | 2977.216 | 3874.478 | 5543.5386
| Total Tax |  | 80801.8439 | 159395.6399 | 385637.0351 | 471858.8593 | 618051.2986

## 12monthProfit
12-month Profit Statement at Year 1
(): represent negative
|  | Remark | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Subtotal
| Revenue |  | 0 | 0 | 0 | 0 | 500000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | 1550000
| (Cost of goods sold) |  | 88700 | 72400 | 116500 | 81000 | 72000 | 88700 | 72400 | 76600 | 72400 | 76600 | 81000 | 72000 | 970300
| Gross profit |  | -88700 | -72400 | -116500 | -81000 | 428000 | 61300 | 77600 | 73400 | 77600 | 73400 | 69000 | 78000 | 579700
| (SG&A expense) |  | 26250 | 26250 | 26250 | 26250 | 26250 | 26250 | 26250 | 26250 | 26250 | 26250 | 26250 | 26250 | 315000
| (Depreciation expense) | Acceleration of depreciation | 5583.34 | 5583.34 | 5583.34 | 5583.34 | 5583.34 | 5583.34 | 5583.34 | 5583.34 | 5583.34 | 5583.34 | 5583.34 | 5583.34 | 67000
| (Amortization expense) | Acceleration&Intangible assets | 16.67 | 16.67 | 16.67 | 16.67 | 16.67 | 16.67 | 16.67 | 16.67 | 16.67 | 16.67 | 16.67 | 16.67 | 200
| Operating profit |  | -120550.01 | -104250.01 | -148350.01 | -112850.01 | 396149.99 | 29449.99 | 45749.99 | 41549.99 | 45749.99 | 41549.99 | 37149.99 | 46149.99 | 197500
| (Interest expense):Borrow 300000 from bank | Annual Interest rate=4.9% | 1225 | 1214.79 | 1204.58 | 1194.37 | 1184.17 | 1173.96 | 1163.75 | 1153.54 | 1143.33 | 1133.12 | 1122.92 | 1112.71 | 14026.24
| Income before tax |  | -121775.01 | -105464.8 | -149554.59 | -114044.38 | 394965.82 | 28276.03 | 44586.24 | 40396.45 | 44606.66 | 40416.87 | 36027.07 | 45037.28 | 183473.76
| (Tax):Corporate Income Tax | Tax rate=25% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80801.8439
| Income from main operations |  | -121775.01 | -105464.8 | -149554.59 | -114044.38 | 394965.82 | 28276.03 | 44586.24 | 40396.45 | 44606.66 | 40416.87 | 36027.07 | 45037.28 | 102671.9161
| Earnings (losses) from other operations, net of tax | About trading securities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Net income |  | -121775.01 | -105464.8 | -149554.59 | -114044.38 | 394965.82 | 28276.03 | 44586.24 | 40396.45 | 44606.66 | 40416.87 | 36027.07 | 45037.28 | 102671.9161

## EarnedValue
Earned Value for Project
| Project tasks | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | PV to Date | Plan Compeleted% | Actual Compeleted% | RV | EV
Preliminary Work | Team Building | Week 1: 5700 | 5700 | 100% | 100% | 100% | 5700 | 38280
| Requirements Analysis | Week 1: 11400 | 11400 | 100% | 95% | 95% | 10830 | 18900
| Fullfill Related Documents | Week 1: 9000 | 9000 | 100% | 85% | 85% | 7650 | 18620
12420
System Design | Structure Design | Week 1: 14100; Week 2: 18900; Week 3: 15400 | 48400 | 100% | 100% | 100% | 48400 | 16840
| Developing Prototype | Week 3: 4600; Week 4: 4600 | 9200 | 100% | 70% | 70% | 6440 | 14950
| UI Design | Week 4: 11500 | 11500 | 100% | 80% | 80% | 9200 | 15065
Coding | Determine Modular Design | Week 5: 8100 | 8100 | 100% | 100% | 100% | 8100
| Information Update Related | Week 5: 9200; Week 6: 9200 | 18400 | 100% | 95% | 95% | 17480
| Dispatching Algorithm Related | Week 6: 6900; Week 7: 4600 | 11500 | 100% | 90% | 90% | 10350
| Financial Figure Update | Week 7: 11500 | 11500 | 100% | 95% | 95% | 10925
Testing | Make Testing Plan | Week 9: 3200
| Unit Test | Week 10: 1200
| Integration Test | Week 10: 1600
| System Test | Week 11: 1200
| Correct System Errors and Defects | Week 11: 1600; Week 12: 400
| Fullfill Related Documents | Week 12: 800
Prpject Management | Make Management Plan | Week 12: 3000
| Documents Management | Week 12: 1000; Week 13: 1000
| Risk Management | Week 13: 3000
| Cost Management | Week 13: 3000
| Fullfill Related Reports | Week 14: 2000
Final Stage | Acceptance Test | Week 14: 2000
| Final Optimization | Week 15: 1600
| Final Deliver | Week 15: 1800
| Service and Maintain | Week 15: 800; Week 16: 2800
|  | Result |  |  | Explanation
Analysis | Project EV as of Week 7 | Week 1: 135075; Week 4: Σ（X5~X16）
| Project PV as of Week 7 | Week 1: 133700; Week 4: See Project Cost Data Sheet
| Project AC as of Week 7 | Week 1: 131400; Week 4: See Project Cost Data Sheet
| CV=EV-AC | Week 1: 3675
| SV=EV-PV | Week 1: 1375
| CPI=EV/AC | Week 1: 102.8%
| SPI=EV/PV | Week 1: 101%
| Estimate at Completion (EAC) | Week 1: 334932.593; Week 4: 344300/CPI
| Estimated time to complete | Week 1: 15.8371; Week 4: 16 Weeks/SPI

## ActualCost
Project Actual COGS
| Project tasks | Estimated Duration | Manager cost/unit (￥) | Menber cost/unit (￥) | Total Manager cost | Total Menber cost(￥) | Other cost (￥) | Cost Remark | Subtotals (￥) | % of Total
Preliminary Work | Team Building | 1 | 1800 | 400 | 1800 | 2000 | 0 | 5 members cost | 3800
| Requirements Analysis | 2 | 1800 | 400 | 3600 | 4000 | 0 | 5 members cost | 7600
| Fullfill Related Documents | 3 | 1000 | 0 | 3000 | 300 | 0 |  | 3300
| ToatalOne |  |  |  | 8400 | 6300 | 0 |  | 14700 | 4.211%
System Design | Structure Design | 13 | 800 | 0 | 10400 | 0 | 0 |  | 10400
| Developing Prototype | 4 | 0 | 400 | 0 | 1600 | 0 |  | 1600
| UI Design | 5 | 0 | 400 | 0 | 2000 | 0 |  | 2000
| ToatalTwo |  |  |  | 10400 | 3600 | 0 |  | 14000 | 4.01%
Coding | Determine Modular Design | 3 | 800 | 0 | 2400 | 0 | 0 |  | 2400
| Information Update Related | 8 | 0 | 400 | 0 | 3200 | 0 |  | 3200
| Dispatching Algorithm Related | 5 | 0 | 400 | 0 | 2000 | 0 |  | 2000
| Financial Figure Update | 15 | 0 | 400 | 0 | 6000 | 0 |  | 6000
| ToatalThree |  |  |  | 2400 | 11200 | 0 |  | 13600 | 3.896%
Testing | Make Testing Plan | 3 | 800 | 0 | 2400 | 0 | 0 |  | 2400
| Unit Test | 2 | 0 | 400 | 0 | 800 | 0 |  | 800
| Integration Test | 3 | 0 | 400 | 0 | 1200 | 0 |  | 1200
| System Test | 3 | 0 | 400 | 0 | 1200 | 0 |  | 1200
| Correct System Errors and Defects | 4 | 0 | 400 | 0 | 1600 | 0 |  | 1600
| Fullfill Related Documents | 3 | 0 | 400 | 0 | 1200 | 0 |  | 1200
| ToatalFour |  |  |  | 2400 | 6000 | 0 |  | 8400 | 2.406%
Prpject Management | Make Management Plan | 3 | 1000 | 0 | 3000 | 0 | 0 |  | 3000
| Documents Management | 3 | 1000 | 0 | 3000 | 0 | 0 |  | 3000
| Risk Management | 3 | 1000 | 0 | 3000 | 0 | 0 |  | 3000
| Cost Management | 3 | 1000 | 0 | 3000 | 0 | 0 |  | 3000
| Fullfill Related Reports | 3 | 1000 | 0 | 3000 | 0 | 0 |  | 3000
| ToatalFive |  |  |  | 15000 | 0 | 0 |  | 15000 | 4.297%
Final Stage | Acceptance Test | 3 | 0 | 400 | 0 | 1200 | 0 |  | 1200
| Final Optimization | 5 | 0 | 400 | 0 | 2000 | 0 |  | 2000
| Final Deliver | 1 | 1800 | 0 | 1800 | 0 | 0 |  | 1800
| Service and Maintain | 20 | 0 | 400 | 0 | 8000 | 0 |  | 8000
| ToatalFive |  |  |  | 1800 | 11200 | 0 |  | 13000 | 3.724%
Total |  |  |  |  | 40400 | 38300 | 0 |  | 78700
Basic Wage |  | 136 | 900 | 1000 | 122400 | 136000 | 0 |  | 258400
Overhead | [6 empty] | 10000 |  | 10000
Other Related Cost | [6 empty] | 2000 |  | 2000
TOTAL |  |  |  |  | 162800 | 174300 | 12000 |  | 349100

## EstimatedCost
Project Estimated Cost
| Project tasks | Estimated Duration | Manager cost/unit (￥) | Menber cost/unit (￥) | Total Manager cost | Total Menber cost(￥) | Other cost (￥) | Cost Remark | Subtotals (￥) | % of Total
Preliminary Work | Team Building | 1 | 1800 | 400 | 1800 | 2000 | 0 | 5 members cost | 3800
| Requirements Analysis | 3 | 1800 | 400 | 5400 | 6000 | 0 | 5 members cost | 11400
| Fullfill Related Documents | 4 | 1000 | 0 | 4000 | 0 | 0 |  | 4000
| ToatalOne |  |  |  | 11200 | 8000 | 0 |  | 19200 | 5.577%
System Design | Structure Design | 10 | 800 | 0 | 8000 | 0 | 0 |  | 8000
| Developing Prototype | 5 | 0 | 400 | 0 | 2000 | 0 |  | 2000
| UI Design | 4 | 0 | 400 | 0 | 1600 | 0 |  | 1600
| ToatalTwo |  |  |  | 8000 | 3600 | 0 |  | 11600 | 3.369%
Coding | Determine Modular Design | 2 | 800 | 0 | 1600 | 0 | 0 |  | 1600
| Information Update Related | 5 | 0 | 400 | 0 | 2000 | 0 |  | 2000
| Dispatching Algorithm Related | 12 | 0 | 400 | 0 | 4800 | 0 |  | 4800
| Financial Figure Update | 15 | 0 | 400 | 0 | 6000 | 0 |  | 6000
| ToatalThree |  |  |  | 1600 | 12800 | 0 |  | 14400 | 4.182%
Testing | Make Testing Plan | 4 | 800 | 0 | 3200 | 0 | 0 |  | 3200
| Unit Test | 3 | 0 | 400 | 0 | 1200 | 0 |  | 1200
| Integration Test | 4 | 0 | 400 | 0 | 1600 | 0 |  | 1600
| System Test | 3 | 0 | 400 | 0 | 1200 | 0 |  | 1200
| Correct System Errors and Defects | 5 | 0 | 400 | 0 | 2000 | 0 |  | 2000
| Fullfill Related Documents | 2 | 0 | 400 | 0 | 800 | 0 |  | 800
| ToatalFour |  |  |  | 3200 | 6800 | 0 |  | 10000 | 2.904%
Prpject Management | Make Management Plan | 3 | 1000 | 0 | 3000 | 0 | 0 |  | 3000
| Documents Management | 2 | 1000 | 0 | 2000 | 0 | 0 |  | 2000
| Risk Management | 3 | 1000 | 0 | 3000 | 0 | 0 |  | 3000
| Cost Management | 3 | 1000 | 0 | 3000 | 0 | 0 |  | 3000
| Fullfill Related Reports | 2 | 1000 | 0 | 2000 | 0 | 0 |  | 2000
| ToatalFive |  |  |  | 13000 | 0 | 0 |  | 13000 | 3.776%
Final Stage | Acceptance Test | 5 | 0 | 400 | 0 | 2000 | 0 |  | 2000
| Final Optimization | 4 | 0 | 400 | 0 | 1600 | 0 |  | 1600
| Final Deliver | 1 | 1800 | 0 | 1800 | 0 | 0 |  | 1800
| Service and Maintain | 15 | 0 | 400 | 0 | 6000 | 0 |  | 6000
| ToatalFive |  |  |  | 1800 | 9600 | 0 |  | 11400 | 3.311%
Subtotal |  |  |  |  | 38800 | 40800 | 0 |  | 79600
Basic Wage |  | 133 | 900 | 1000 | 119700 | 133000 | 0 |  | 252700
Overhead | [6 empty] | 10000 |  | 10000
Other Related Cost | [6 empty] | 2000 |  | 2000
TOTAL |  |  |  |  | 158500 | 173800 | 12000 |  | 344300

## EVChart
Project EV Chart
| Project Process Weekly | Estimated Cost | Actual Cost | Cumulative PV | Cumulative AC | EV | Cumulative EV
| 1 | 32500 | 28800 | 32500 | 28800 | 38280 | 38280
| 2 | 18900 | 18900 | 51400 | 47700 | 18900 | 57180
| 3 | 17100 | 18100 | 68500 | 65800 | 18620 | 75800
| 4 | 16900 | 16100 | 85400 | 81900 | 12420 | 88220
| 5 | 16100 | 17300 | 101500 | 99200 | 16840 | 105060
| 6 | 16100 | 16100 | 117600 | 115300 | 14950 | 120010
| 7 | 16100 | 16100 | 133700 | 131400 | 15065 | 135075
| 8 | 16100 |  | 149800
| 9 | 18100 |  | 167900
| 10 | 16100 |  | 184000
| 11 | 16500 |  | 200500
| 12 | 19100 |  | 219600
| 13 | 21300 |  | 240900
| 14 | 16100 |  | 257000
| 15 | 18100 |  | 275100
| 16 | 17300 |  | 292400

## DateSheet
Project Cost Data Sheet
|  |  |  | Weekly Basic Wage | 13300
| Project Process Weekly | Estimated Cost | Actual Cost | Estimated Cumulative Cost | Actual Cumulative Cost
| 1 | 32500 | 28800 | 32500 | 28800
| 2 | 18900 | 18900 | 51400 | 47700
| 3 | 17100 | 18100 | 68500 | 65800
| 4 | 16900 | 16100 | 85400 | 81900
| 5 | 16100 | 17300 | 101500 | 99200
| 6 | 16100 | 16100 | 117600 | 115300
| 7 | 16100 | 16100 | 133700 | 131400
| 8 | 16100 | 16100 | 149800 | 147500
| 9 | 18100 | 17300 | 167900 | 164800
| 10 | 16100 | 16100 | 184000 | 180900
| 11 | 16500 | 16100 | 200500 | 197000
| 12 | 19100 | 20300 | 219600 | 217300
| 13 | 21300 | 20300 | 240900 | 237600
| 14 | 16100 | 16700 | 257000 | 254300
| 15 | 18100 | 17500 | 275100 | 271800
| 16 | 17300 | 20300 | 292400 | 292100

## Break-Even
Break-Even Analysis
Discount rate: 10.6%
|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Cost | Costs | 900000 | 1410128.0839 | 1868251.8799 | 2063023.2751 | 2414773.6993 | 3054597.5386
| Discount factor | 1 | 1 | 0.90416 | 0.8175 | 0.73915 | 0.66831
| Discounted costs | 900000 | 1410128.0839 | 1689196.9981 | 1686529.2348 | 1784888.3551 | 2041425.2849
| Cumulative costs | 900000 | 2310128.0839 | 3999325.082 | 5685854.3168 | 7470742.672 | 9512167.9569
Benefits | Benefits | 0 | 1575686.3264 | 2533054.9264 | 2402591.2464 | 2829537.3304 | 3394263.3556
| Discount factor | 1 | 1 | 0.90416 | 0.8175 | 0.73915 | 0.66831
| Discounted benefits | 0 | 1575686.3264 | 2290284.7436 | 1964127.32 | 2091462.3316 | 2268428.1481
| Cumulative benefits | 0 | 1575686.3264 | 3865971.07 | 5830098.39 | 7921560.7216 | 10189988.8696
| Discounted benefits-Discounted costs | -900000 | 165558.2425 | 601087.7455 | 277598.0852 | 306573.9764 | 227002.8632
| Benefits-Costs | -900000 | 165558.2425 | 664803.0465 | 339567.9713 | 414763.6311 | 339665.817
| Cumulative benefits - Cumulative costs | -900000 | -734441.7575 | -133354.012 | 144244.0731 | 450818.0496 | 677820.9128
|  |  | Consequence | Explanation
| NPV |  | 677820.9128 | I17 or Σ(D15~I15)
| IRR |  | 22.77% | Make Costs=Benefits after discounting
| Payback Year |  | Year 3 | F17<0, G17>0

## Sensitivity
Sensitivity Analysis in Year 2
| Undiscounted Value | % change in UV | PW | % change in PW
Revenue | 2279749.4338 | -10% | 381723.1483 | -38.1%
| 2406402.1801 | -5% | 499211.7812 | -19.05%
| 2533054.9264 | 0% | 616700.4142 | 0%
| 2659707.6727 | 5% | 734189.0471 | 19.05%
| 2786360.419 | 10% | 851677.6801 | 38.1%
COGS | 873270 | -10% | 706709.6906 | 14.6%
| 921785 | -5% | 661705.0524 | 7.298%
| 970300 | 0% | 616700.4142 | 0%
| 1018815 | 5% | 571695.776 | -7.298%
| 1067330 | 10% | 526691.1378 | -14.6%
SGA&DA | 307962 | -10% | 648442.5292 | 5.147%
| 325071 | -5% | 632571.4717 | 2.574%
| 342180 | 0% | 616700.4142 | 0%
| 359289 | 5% | 600829.3567 | -2.574%
| 376398 | 10% | 584958.2992 | -5.147%