## Sheet1
Serial Numver | Activity | Optimistic Time | Most Likely Time | Pessimistic time | Expected Duration | Standard Deviations
A | Requirement Analysis | 1 | 2 | 3 | 2 | 0.33
B | User Interface Design | 2 | 3 | 5 | 3.17 | 0.5
C | Data Design | 1.5 | 2 | 3 | 2.09 | 0.25
D | Architecture Design | 1.5 | 2 | 4 | 2.25 | 0.42
E | Interface Design | 2 | 3 | 5 | 3.17 | 0.5
F | Design Review | 1 | 2 | 2.5 | 1.92 | 0.25
G | Front-end Implementation | 3 | 4 | 5 | 4 | 0.33
H | Back-end Implementation | 3.5 | 5 | 6 | 4.92 | 0.42
I | Software Testing | 1.5 | 2 | 3 | 2.09 | 0.25
J | User Manual | 1 | 3 | 4 | 2.83 | 0.5
K | Deployment & System Testing | 2 | 3 | 4 | 3 | 0.33
L | User Training | 0.5 | 1 | 2 | 1.42 | 0.25