## Sheet1
RISK RECORD | [5 empty] | RISK RECORD | [5 empty] | RISK RECORD | [5 empty] | RISK RECORD | [5 empty] | RISK RECORD | [5 empty] | RISK RECORD | [5 empty] | RISK RECORD | [5 empty] | RISK RECORD
Risk id | R1 | Risk title | Team members did not communicate well |  |  | Risk id | R2 | Risk title | Technology adopted is flawed |  |  | Risk id | R3 | Risk title | Project management structure is not clear |  |  | Risk id | R4 | Risk title | Code integration issues |  |  | Risk id | R5 | Risk title | Personnel changes |  |  | Risk id | R6 | Risk title | Implementation tools do not meet the requirements |  |  | Risk id | R7 | Risk title | Change to requirements specification during coding |  |  | Risk id | R8 | Risk title | System quality and performance risks
Owner | Zhe Zhang | Data raised | 2019-04-01 | Status | first update | Owner | Kaixin Chen | Data raised | 2019-04-03 | Status | second update | Owner | Di Bu | Data raised | 2019-04-09 | Status | first update | Owner | Zhe Zhang | Data raised | 2019-04-09 | Status | third update | Owner | Zhe Zhang | Data raised | 2019-04-09 | Status | third update | Owner | Kaixin Chen | Data raised | 2019-04-02 | Status | first update | Owner | Di Bu | Data raised | 2019-03-21 | Status | second update | Owner | Zhe Zhang | Data raised | 2019-04-09 | Status | none update
Risk Description: Due to the low enthusiasm or participation among members, the communication is not in place. | [5 empty] | Risk Description: There are technical flaws in the programming techniques or frameworks used during the project. | [5 empty] | Risk Description: There is no clear understanding of the overall management structure of the project and no clear explanation. | [5 empty] | Risk Description: Because of the differences between the code module division and the coding habits of the members, the final code integration lags behind. | [5 empty] | Risk Description: A condition in which a group member cannot continue to work for some reason, resulting in the absence of a member. | [5 empty] | Risk Description: Whether the management tools, development tools and test tools that must be used in the project development and implementation process can be in place in time and whether the tool versions in place meet the project requirements. | [5 empty] | Risk Description: Users may frequently propose new requirements or modify existing requirements. | [5 empty] | Risk Description: Users will have a high demand for software quality and the software system will have a high demand for performance.
Impact Description: Project progress is slow, which drags down the progress of the project. | [5 empty] | Impact Description: The project is in trouble and may not be able to proceed, requiring an alternative approach. | [5 empty] | Impact Description: Work chaos, slow progress. | [5 empty] | Impact Description: The project process is controlled and a lot of time is spent dealing with coding differences. | [5 empty] | Impact Description: It can affect the project schedule and delay the progress, and it can cause the project to be unable to continue or even die. | [5 empty] | Impact Description: Additional time will be spent reselecting and implementing tools to slow down the project. | [5 empty] | Impact Description: At the very least, new work needs to be added, and at the very least, the whole project may have to be overhauled. | [5 empty] | Impact Description: /
Recommended risk mitigation: Agree on the way of communication at the beginning of the project and regularly communicate the schedule of work progress. If necessary, take minutes of the meeting to reduce the possibility of it. | [5 empty] | Recommended risk mitigation: When it comes to the risk bottleneck, turn the head and select the experienced or familiar technology. At the same time, a team member can study and learn the new technology, which lays the foundation for the project implementation. | [5 empty] | Recommended risk mitigation: Formulate the management structure in advance and let a team member manage and maintain the management structure. | [5 empty] | Recommended risk mitigation: To start the project code before the writing of a good agreement on the development environment and code specification, annotation specification, etc., the development process, incremental development and integration, reduce the final workload. | [5 empty] | Recommended risk mitigation: Get everyone involved in the core of the project and make sure that changes in people don't derail the project. | [5 empty] | Recommended risk mitigation: Identify and implement the source of the tools at the start of the project, while finding the necessary alternative tools, and implement the tools in place before they need to be used. | [5 empty] | Recommended risk mitigation: Identify and implement the source of the tools at the start of the project, while finding the necessary alternative tools, and implement the tools in place before they need to be used. | [5 empty] | Recommended risk mitigation: In the regular meeting of the team, the work results are exchanged, the results are checked and reviewed, and the performance test is carried out. After the performance test meets the indicators, the follow-up work is carried out.
Probability/impact values: 5 / 5 | [5 empty] | Probability/impact values: 3 / 10 | [5 empty] | Probability/impact values: 3 / 4 | [5 empty] | Probability/impact values: 4 / 5 | [5 empty] | Probability/impact values: 2 / 8 | [5 empty] | Probability/impact values: 2 / 4 | [5 empty] | Probability/impact values: 8 / 8 | [5 empty] | Probability/impact values: 6 / 7
|  | Probability | Impact |  |  |  |  | Probability | Impact |  |  |  |  | Probability | Impact |  |  |  |  | Probability | Impact |  |  |  |  | Probability | Impact |  |  |  |  | Probability | Impact |  |  |  |  | Probability | Impact |  |  |  |  | Probability | Impact
|  |  | Cost | Duratioin | Quality |  |  |  | Cost | Duratioin | Quality |  |  |  | Cost | Duratioin | Quality |  |  |  | Cost | Duratioin | Quality |  |  |  | Cost | Duratioin | Quality |  |  |  | Cost | Duratioin | Quality |  |  |  | Cost | Duratioin | Quality |  |  |  | Cost | Duratioin | Quality
Pre-mitigation |  | 25 | 2 | 7 | 5 | Pre-mitigation |  | 30 | 6 | 6 | 7 | Pre-mitigation |  | 12 | 3 | 3 | 3 | Pre-mitigation |  | 8 | 3 | 3 | 2 | Pre-mitigation |  | 16 | 4 | 4 | 4 | Pre-mitigation |  | 16 | 5 | 5 | 5 | Pre-mitigation |  | 64 | 8 | 7 | 7 | Pre-mitigation |  | 42 | 7 | 8 | 8
Post-mitigation |  | 10 | 1 | 3 | 3 | Post-mitigation |  | 8 | 2 | 3 | 3 | Post-mitigation |  | 5 | 1 | 2 | 1 | Post-mitigation |  | 2 | 1 | 1 | 1 | Post-mitigation |  | / | / | / | / | Post-mitigation |  | 10 | 3 | 1 | 3 | Post-mitigation |  | 8 | 2 | 2 | 2 | Post-mitigation |  | / | / | / | /
Incident/action history | [5 empty] | Incident/action history | [5 empty] | Incident/action history | [5 empty] | Incident/action history | [5 empty] | Incident/action history | [5 empty] | Incident/action history | [5 empty] | Incident/action history | [5 empty] | Incident/action history
Date | Incident/action |  |  | Actor | Outcome/comment | Date | Incident/action |  |  | Actor | Outcome/comment | Date | Incident/action |  |  | Actor | Outcome/comment | Date | Incident/action |  |  | Actor | Outcome/comment | Date | Incident/action |  |  | Actor | Outcome/comment | Date | Incident/action |  |  | Actor | Outcome/comment | Date | Incident/action |  |  | Actor | Outcome/comment | Date | Incident/action |  |  | Actor | Outcome/comment
2019-04-05 | Agree that every Saturday night is the regular meeting time, need to summarize the work of the week |  |  | All team members | If necessary, a written record should be made | 2019-04-08 | Using SpringBoot framework for back-end; Using origin framework for front-end |  |  | Di Bu | / | 2019-04-14 | Make sure project management structure and maintance and develop by Kaixin Chen |  |  | All team member | / | 2019/4/10 2019/4/15 | Integrate currently code for personal responsibility |  |  | All team member | Decrease work for later code integration | / | / |  |  | / | / | 2019-04-16 | IDE for front-end we choose JetBrains WebStorm; IDE for back-end we choose JetBrains IntelliJ IDEA; Database we choose MySQL Workbench |  |  | Di Bu | Decrease work later | 2019/4/1 2019/4/10 | Requirement changing |  |  | Zhe Zhang | / | / | / |  |  | / | /