## Sheet1
Risk probability level
score | probability range | level | description
10 | 90% ~ 1 | High | Almost certainly
9 | 80% ~ 90%
8 | 70% ~ 80% | Significant | Very likely
7 | 60% ~ 70%
6 | 50% ~ 60% | Moderate | Likely
5 | 40% ~ 50%
4 | 30% ~ 40%
3 | 20% ~ 30% | Low | Almost impossible
2 | 10% ~ 20%
1 | 0 ~ 10%
Risk impact level
|  |  |  | score | level | description
|  |  |  | 10 | High | Lead to the failure
9
|  |  |  | 8 | Significant | Create a big negative impact
7
|  |  |  | 6 | Moderate | Some influences on the project
5
4
|  |  |  | 3 | Low | The negative impact is almost negligible
2
1
Risk level decision
[7 empty] | level(cardinal) | level(ordinal) | result
[7 empty] | 64~100 | High | Can't accept
[7 empty] | 36~64 | Significant | Need to make a decision
[7 empty] | 9~36 | Moderate | Need to be reviewed
[7 empty] | 0~9 | Low | Can be neglected